## Template Overview
Family Reunion Event Run of Show
Use to plan the tactical activities required for setting up, delivering, and taking down your family reunion event
© Copyright 2023 Danny Loomans. All rights reserved. Submit Questions or Feedback at uncommongenealogist.com/templates.
What You Need: | Template Guidance:
Access to a printer or copy machine if you decide that printing your storyboard will help with the successful execution of the event | Familiarize yourself with the structure of the next tab, including the key columns and the various recommended Run of Show tasks Edit or delete irrelevant example tasks by clicking in the cell or selecting the row to delete it (right click) Identify items that are not included on the Run of Show that should be; type the task in one of the many blank rows on the sheet Assign each task an estimate duration in minutes in Column E; this estimate does not have to be exact; make it easier by being conservative and identifying durations in 15-minute increments Add the date the task should be completed in Column B Add a location for the task to be completed in Column G; this will help coordinate the sequence of errands and activities Filter on Column B by selecting the dropdown arrow and checking the box of a single date; the nprioritize the tasks that appear aligned with that date, determining which should happen first, second, and so forth (identify this number in Column C) Add a time for each of those tasks to be completed in Column D Record any notes in Column I that ar erelevant to the task's successful copmletion (like an order number for picking up food items or the location of specific supplies) Assign a volunteer to each task in Column H Sort the tasks by date and time using the filter dropdown arrow; adjust and enhance the Run of Show as needed

## Event Run of Show
Family Reunion Event Run of Show
Date | Order | Time | Duration | Task Description | Location | Volunteer / Owner | Additional Notes
Vist event venue site for evening preparation activities and cleaning
Load vehicles with supplies, food, and materials
Drive to the event venue site
Unload supplies, food, and materials and event venue site; place all supplies in designated area for unpacking
Pick up food and refreshment items from vendor location
Pick up dessert food items at the vendor location
Cut vegetables and arrange on vegetable tray
Prepare condiments by placing them in bottles, ramekins, etc.
Prepare food items not being catered / picked up
Pick up purchased flowers from the florist vendor location
Set up tables according to the defined reunion space layout design
Place tablecloths on tables, including table clip fasteners
Set up 'Explore Our Story' and photo board exhibit space
Set up and secure the family tree panels
Stake directional lawn signage around the reunion perimeter
Hang and decorate any décor in the space such as streamers, balloons, and event banners / large signage
Place flowers into vases and arrange table centerpieces
Set up the food and refreshments table with food items in serving dishes
Place food signage in front of the appropriate food items; secure with tape if outdoors and / or required
Set up the check in and welcome table
Arrange name tags and other reunion welcome information on table
Perform final walkthrough for garbage and to double check set up configuration and requirements
Prepare beverage station and final food items -- checking ice in the coolers, plates, utensils, cups, etc.
Capture pictures of the event setup before any guests arrive
Move remaining items, including supply bins, and trash to vehicles
Package remaining food and box refreshments as part of take down
Remove centerpieces and tablecloths from tables
Package artifacts and photographs from 'Explore Our Story' and photo board exhibit sections of the event
Take down any hanging signage, staked signage, and décor
Package remaining supplies and materials
Wipe down tables, sweep floor, and dispose of garbage items
Load vehicles with all reuion materials and supplies
Depart event venue site